## Ark2
Lofthus frukt og saft
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
First Draft
| Preproduction Meeting | 2020-01-06 | 2020-01-06 | 1 | All | 0% | bar: WEEK 2 M; WEEK 3 T; WEEK 3 Th to WEEK 3 F; WEEK 5 T; WEEK 5 Th to WEEK 5 F
| Competitor check | 2020-01-07 | 2020-01-07 | 1 | Jonn | 0% | bar: WEEK 2 T; WEEK 3 T; WEEK 3 Th to WEEK 3 F; WEEK 5 T; WEEK 5 Th to WEEK 5 F
| Scetch landing page copy | 2020-01-08 | 2020-01-10 | 3 | Jonn | 0% | bar: WEEK 2 W to WEEK 3 T; WEEK 3 Th to WEEK 3 F; WEEK 5 T; WEEK 5 Th to WEEK 5 F
| Review Landing Page Design | 2020-01-13 | 2020-01-14 | 2 | Jonn | 0% | bar: WEEK 5 T; WEEK 5 Th to WEEK 5 F
| Build Landing Page basics | 2020-01-15 | 2020-01-17 | 3 | Jonn | 0% | bar: WEEK 3 T to WEEK 3 F; WEEK 5 T; WEEK 5 Th to WEEK 5 F
| Build CSS | 2020-01-20 | 2020-01-22 | 3 | Jonn | 0% | bar: WEEK 3 T; WEEK 3 Th to WEEK 4 W; WEEK 5 T; WEEK 5 Th to WEEK 5 F
| Assemble Landingpage/CSS | 2020-01-23 | 2020-01-28 | 4 | Jonn/Ivar | 0% | bar: WEEK 3 T; WEEK 3 Th to WEEK 3 F; WEEK 4 Th to WEEK 5 T; WEEK 5 Th to WEEK 5 F
Gather Pictures/text
| Pictures | 2020-01-13 | 2020-01-14 | 2 | Brian photo | 0% | bar: WEEK 3 M to WEEK 3 T; WEEK 3 Th to WEEK 3 F; WEEK 5 T; WEEK 5 Th to WEEK 5 F
| Rework pictures | 2020-01-14 | 2020-01-17 | 4 | Brian photo | 0% | bar: WEEK 3 T to WEEK 3 F; WEEK 5 T; WEEK 5 Th to WEEK 5 F
| Make the text for the wepage | 2020-01-17 | 2020-01-21 | 3 | Brian photo | 0% | bar: WEEK 3 T; WEEK 3 Th to WEEK 4 T; WEEK 5 T; WEEK 5 Th to WEEK 5 F
| Get approval for pictures used | 2020-01-20 | 2020-01-20 | 1 | Ivar | 0% | bar: WEEK 3 T; WEEK 3 Th to WEEK 4 M; WEEK 5 T; WEEK 5 Th to WEEK 5 F
Technical integrations
| Landingpage Ecommerce | 2020-01-27 | 2020-01-31 | 5 | Ecomm-inc | 0% | bar: WEEK 3 T; WEEK 3 Th to WEEK 3 F
| Source/implement payment solutions | 2020-01-28 | 2020-01-31 | 4 | Ecomm-inc | 0% | bar: WEEK 3 T; WEEK 3 Th to WEEK 3 F; WEEK 5 T to WEEK 5 F
| Make product pages Ecommecre inc text | 2020-02-03 | 2020-02-07 | 5 | Ecomm-inc | 0% | bar: WEEK 3 T; WEEK 3 Th to WEEK 3 F; WEEK 5 T; WEEK 5 Th to WEEK 6 F
| Finish landingpage | 2020-02-06 | 2020-02-07 | 2 | Ecomm-inc | 0% | bar: WEEK 3 T; WEEK 3 Th to WEEK 3 F; WEEK 5 T; WEEK 5 Th to WEEK 5 F; WEEK 6 Th to WEEK 6 F
Assembly/testing
| Complete about us/Contact | 2020-01-27 | 2020-01-31 | 5 | Jonn | 0% | bar: WEEK 3 T; WEEK 3 Th to WEEK 3 F
| Assemble webpage w/CSS | 2020-02-03 | 2020-02-07 | 5 | Ivar | 0% | bar: WEEK 3 T; WEEK 3 Th to WEEK 3 F; WEEK 5 T; WEEK 5 Th to WEEK 6 F
| Technical testing | 2020-02-10 | 2020-02-12 | 3 | Jonn | 0% | bar: WEEK 3 T; WEEK 3 Th to WEEK 3 F; WEEK 5 T; WEEK 5 Th to WEEK 5 F; WEEK 6 M to WEEK 6 W
| Rework issues | 2020-02-13 | 2020-02-17 | 3 | Ivar | 0% | bar: WEEK 3 T; WEEK 3 Th to WEEK 3 F; WEEK 5 T; WEEK 5 Th to WEEK 5 F; WEEK 6 Th to WEEK 7 M
Finish product/GO LIVE
| Present finished product | 2020-02-18 | 2020-02-18 | 1 | Ivar | 0% | bar: WEEK 3 T; WEEK 3 Th to WEEK 3 F; WEEK 5 T; WEEK 5 Th to WEEK 5 F; WEEK 7 T
| Fix eventually design issues | 2020-02-19 | 2020-02-19 | 1 | Jonn | 0% | bar: WEEK 3 T; WEEK 3 Th to WEEK 3 F; WEEK 5 T; WEEK 5 Th to WEEK 5 F; WEEK 7 W
| GO LIVE! | 2020-02-20 | 2020-02-20 | 1 | All | 0% | bar: WEEK 3 T; WEEK 3 Th to WEEK 3 F; WEEK 5 T; WEEK 5 Th to WEEK 5 F; WEEK 7 Th
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])